## Slide 1
DELOITTE · PORTFOLIOIQ
Project Portfolio
Executive Dashboard.
Reporting period | January 2026
ISSUE DATE
01 FEBRUARY 2026
PREPARED BY
DELOITTE CONSULTING
AI-powered insight. Leadership-ready reporting.

## Slide 2
01 — PORTFOLIO SNAPSHOT
Reporting Period | January 2026
Portfolio Snapshot
High-level status across 201 projects as of January 2026
Energy Client Portfolio Executive Summary | January 2026
Page 1
201
PORTFOLIO SCOPE
100 active · 101 pending
25
COMPLETED
of 100 active
12
OVERDUE
12% of active
€39.4M
FY2026 COMMITTED BUDGET
€21.5M active · €18.0M pending
16.5%
YEAR-TO-DATE SPEND
€6.5M of €39.4M (PR+PO)
SCHEDULE OVERVIEW
81% of active portfolio is delayed or lacking schedule visibility.
Only 19 of 100 projects confirmed on track.
22 delayed >20% · 58 with no baseline established
BUDGET STATUS
96% within budget — strong fiscal discipline.
4 projects with Budget Overrun Risk (up to 300% of FY2026 Budget).
€5.9M exposure across 11 Red/Amber flagged projects.
KEY TAKEAWAY
Portfolio performance shows mixed results with key risks identified.
81% of active portfolio shows schedule risk: 22 major delays and 12 overdue projects. Budget adherence remains strong at 96%, yet €5.9M exposure across 11 Red/Amber projects requires attention.
Immediate action required: prioritize overdue and delayed projects to mitigate risks and ensure schedule recovery.

## Slide 3
02a — DEEP DIVE: SCHEDULE HEALTH
Reporting Period | January 2026
Energy Client Portfolio Executive Summary | January 2026
Page 2
Schedule Health
Schedule distribution across 100 active projects and key risk areas
Chart: 
| On Track | Delayed ≤20% | Delayed >20% | No Baseline
Schedule Health | 19 | 1 | 22 | 58
KEY SCHEDULE RISKS
● Schedule health at 81% with 22 activities delayed >20% — critical risk to overall project timeline and €39.4M budget delivery
● 101 pending tasks (50% of total 201) creates HIGH bottleneck risk; 58 activities lack baseline, impacting schedule predictability
● 12 overdue activities (6% of total) and €5.9M financial exposure with 16.5% YTD spend acceleration indicates MEDIUM cost control risk
REQUIRED ACTION
Establish baselines for all projects by June 2026.
Owner: Portfolio PMO Lead | Target: Jun 2026
19
On Track
1
Delayed ≤20%
22
Delayed >20%
58
No Baseline

## Slide 4
02b — DEEP DIVE: BUDGET HEALTH
Reporting Period | January 2026
Energy Client Portfolio Executive Summary | January 2026
Page 3
Budget Health
FY2026 Budget Distribution by investment category and key budget health indicators
Chart: 
| Long Term Maint. | Financial Perf. | Betterment | Safety / Reg.
Budget Category | 21.5 | 13.4 | 3.9 | 0.7
Long Term Maintenance
€21.5M · 54%
Financial Performance
€13.4M · 34%
Betterment
€3.9M · 10%
Safety / Regulatory
€0.7M · 2%
KEY BUDGET INSIGHTS
● 189 projects within budget out of 201 total—strong cost control with only 12 overdue items flagged for review.
● Overrun risk: HIGH with 11 RAG-flagged projects and 22 activities delayed >20%, requiring immediate mitigation across €5.9M exposure.
● Total exposure €5.9M against €39.4M budget (15% utilization)—YTD spend at 16.5% indicates healthy pacing but 58 projects lack baseline estimates.
● Long Term Maintenance dominates at €21.5M (54% of budget), followed by Financial Performance €13.4M (34%)—core operations well-resourced but Betterment initiatives remain underfunded at €3.9M (10%).

## Slide 5
03 — INTERVENTION REQUIRED FROM LEADERSHIP
Reporting Period | January 2026
Energy Client Portfolio Executive Summary | January 2026
Page 4
Decisions or attention required from Leadership
4 items require management attention or a leadership decision before the next reporting period
D1 | CRITICAL PRIORITIZE DELAYED PROJECTS
Approve recovery plans for 22 delayed projects.
22 projects are significantly delayed, representing 22% of active projects. This impacts portfolio delivery timelines and requires immediate recovery planning by Q2 2026.
Owner: Portfolio PMO Lead | Target: Jun 2026
D2 | HIGH ESTABLISH PROJECT BASELINES
Mandate baselines for 58 active projects.
58 active projects lack baselines, preventing accurate tracking and forecasting. This represents 58% of active projects and must be resolved by Q2 2026.
Owner: Portfolio PMO Lead | Target: Jun 2026
D3 | MEDIUM MONITOR BUDGET EXPOSURE
Enforce weekly monitoring of €5.9M exposure.
13 RAG items, including 4 flagged for overrun risk, contribute to €5.9M budget exposure. Strong fiscal discipline is needed to maintain 96% budget adherence.
Owner: Finance & Control | Target: Dec 2026
D4 | LOW ACCELERATE TURBINE INSPECTION
Conduct root-cause review for turbine delays.
The Steam Turbine Major Inspection is only 5% complete with a €4.5M budget at risk. Accelerating execution by Q1 2027 will mitigate further delays.
Owner: Thessaloniki | Target: Jan 2027

## Slide 6
04 — PROJECTS AT RISK
Projects at Risk
Top 5 flagged projects needing decisions (€5.9M combined exposure across all 13 Red/Amber). Full list in Appendix.
RAG | Project | Owner | Target Go-Live | CY Budget | Progress | Highlights & Action
Red | ST Hydraulic Pumps Replacement | Thisvi | TBD | €168k | 5% | 5% complete · €168k · target TBD · Action: Escalate to PM
Red | 3D HRSG Scanning | Technical Services | Dec 2025 | €0 | 0% | 0% complete · €0 budget · Action: Confirm scope and start
Amber | Steam Turbine Major Inspection | Thessaloniki | Jan 2027 | €4.5M | 5% | 5% complete · €4.5M · target Jan 2027 · Action: Escalate to PM
Amber | TIL001121 Auto Tune System Installation at Thisvi Plant | Thisvi | TBD | €500k | 10% | 10% complete · €500k · target TBD · Action: Escalate to PM
Amber | Replacement of High Pressure (HP) and Hot Reheat (HRH) Steam turbine valves. | Thessaloniki | Feb 2026 | €360k | 10% | 10% complete · €360k · target Feb 2026 · Action: Escalate to PM
+ 8 additional Red/Amber projects (2 data quality issues + 6 nearing completion) — see Appendix A.1 for full list
Energy Client Portfolio Executive Summary | January 2026
Page 4
Reporting Period | January 2026

## Slide 7
05 — KEY RISKS
Key Risks
Issues requiring management attention and recommended next steps
# | Type | Description / Impact | Severity | Status | Mitigation Action | Owner | Target
1 | R | Schedule Slippage Risk – 22 activities delayed >20% and 81% schedule performance indicate critical path vulnerability. At current trajectory, €39.4M budget exposure may require scope/timeline adjustments. | HIGH | Active | Implement weekly critical path reviews; allocate €1.2M schedule recovery buffer; escalate 22 delayed tasks to workstream owners for recovery plans. | Portfolio Schedule Manager | 2026-03-31
2 | I | Budget Baseline Deficiency – 58 initiatives lack defined baselines (29% of active portfolio). Prevents accurate variance tracking and cost control across €39.4M total budget with 16.5% YTD spend. | CRITICAL | Pending | Enforce baseline completion for all 58 initiatives by Q1 2026; conduct €5.9M exposure reconciliation; implement monthly forecast reforecasting discipline. | Portfolio CFO / Finance Lead | 2026-02-28
3 | R | Budget Overrun Exposure – €5.9M exposure against €39.4M budget (15% at-risk); 12 overdue items and 11 RAG-flagged initiatives signal cost control deterioration. YTD 16.5% spend suggests acceleration risk. | HIGH | Active | Establish €2.0M contingency reserve; institute bi-weekly cost/schedule health reviews; implement change control freeze on non-critical scope through Q2 2026. | Portfolio Controller | 2026-04-30
Type: I = Issue R = Risk
Energy Client Portfolio Executive Summary | January 2026
Page 5
Reporting Period | January 2026

## Slide 8
APPENDIX A.1 — RED & AMBER FULL LIST
Red & Amber Full List
All 13 projects with Red or Amber RAG status including highlights and recommended actions
RAG | Code | Project | Owner | Go-Live | Budget | % | Highlights / Action
Red | 2025-00144 | ST Hydraulic Pumps Replacement | Thisvi | TBD | €168k | 5% | 5% complete · €168k · target TBD · Action: Escalate to PM
Red | 2025-00159 | 3D HRSG Scanning | Technical Services | Dec 2025 | €0 | 0% | 0% complete · €0 budget · Action: Confirm scope and start
Amber | 2025-00127 | Steam Turbine Major Inspection | Thessaloniki | Jan 2027 | €4.5M | 5% | 5% complete · €4.5M · target Jan 2027 · Action: Escalate to PM
Amber | 2025-00164 | TIL001121 Auto Tune System Installation at Thisvi Plant | Thisvi | TBD | €500k | 10% | 10% complete · €500k · target TBD · Action: Escalate to PM
Amber | 2025-00188 | Replacement of High Pressure (HP) and Hot Reheat (HRH) Steam turbine valves. | Thessaloniki | Feb 2026 | €360k | 10% | 10% complete · €360k · target Feb 2026 · Action: Escalate to PM
Amber | 2025-00113 | HRSG HRH Vent stop valve replacement & part of pipeline replacement | Thessaloniki | TBD | €115k | 10% | 10% complete · €115k · target TBD · Action: Escalate to PM
Amber | 2025-00118 | Fuel Gas AGI Flow computer and flow meters replacement | Thessaloniki | TBD | €110k | 80% | 80% complete · €110k budget · Action: Push to closeout
Amber | 2025-00157 | Evaporative Cooling Tower (ECT) supply & installation | Thisvi | Dec 2025 | €60k | 5% | 5% complete · €60k · target Dec 2025 · Action: Escalate to PM
Amber | 2025-00116 | ST Lube oil mist eliminator upgrade | Thessaloniki | TBD | €57k | 70% | 70% complete · €57k · target TBD · Action: Escalate to PM
Amber | 2025-00156 | Addition of oil moisture analyser in GT & ST lube oil tanks | Thisvi | TBD | €30k | 20% | 20% complete · €30k · target TBD · Action: Escalate to PM
Amber | 2025-00117 | Desuperheaters replacement (HP intermediate and HRH Final) | Thessaloniki | TBD | €0 | 90% | 90% complete · €0 budget · Action: Push to closeout
Energy Client Portfolio Executive Summary | January 2026
Page 6
Reporting Period | January 2026

## Slide 9
APPENDIX A.2 — PROJECT TIMELINE
Project Timeline (1/2)
13 Red/Amber projects mapped on a 2025–2026 monthly timeline (% = current completion)
Project | % | J25 | F | M | A | M | J | J | A | S | O | N | D | J26 | F | M | A | M | J | J | A | S | O | N | D
ST Hydraulic Pumps Repla | 5% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
myElpedison Redesign/Rel | 5% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3D HRSG Scanning | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Strategic spare parts ( | 95% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Steam Turbine Major Insp | 5% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
TIL001121 Auto Tune Syst | 10% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Replacement of High Pres | 10% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HRSG HRH Vent stop valve | 10% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Fuel Gas AGI Flow comput | 80% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Evaporative Cooling Towe | 5% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
ST Lube oil mist elimina | 70% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Addition of oil moisture | 20% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Legend: ■ Green ■ Amber ■ Red Solid = completed • Light = planned • Today: Jan 2026
Energy Client Portfolio Executive Summary | January 2026
Page 7
Reporting Period | January 2026

## Slide 10
APPENDIX A.2 — PROJECT TIMELINE
Project Timeline (2/2)
13 Red/Amber projects mapped on a 2025–2026 monthly timeline (% = current completion)
Project | % | J25 | F | M | A | M | J | J | A | S | O | N | D | J26 | F | M | A | M | J | J | A | S | O | N | D
Desuperheaters replaceme | 90% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Legend: ■ Green ■ Amber ■ Red Solid = completed • Light = planned • Today: Jan 2026
Energy Client Portfolio Executive Summary | January 2026
Page 7
Reporting Period | January 2026