## Slide 1
DELOITTE × ENERWAVE
Project Portfolio.
Executive Dashboard
Reporting period · December 2025
AI-GENERATED EXECUTIVE REPORTING
Written, designed and self-reviewed by AI

## Slide 2
Portfolio IQ.
DELOITTE AI & DATA
DELOITTE × ENERWAVE
02 / 08
01 · PORTFOLIO SNAPSHOT
Portfolio Snapshot.
96 active projects · 10 flagged · €0.9M exposure
201
Total projects
96 active · 105 pending
24
Completed
lifetime
4
Overdue
4% of active
€39.4M
Committed budget
€18.0M active · €21.4M pending
3.3%
YTD Spend
€1.3M of €39.4M
SCHEDULE HEALTH
16 On Track
1 Delayed ≤20%
21 Delayed >20%
58 No Baseline
KEY TAKEAWAY
Portfolio tracking shows operational maturity with execution gaps requiring immediate intervention.
Of 201 total initiatives, 96 are active with 105 pending and concerning 4 overdue items. Budget utilization stands at 3.3% YTD against €39.4M allocation, while 10 RAG-flagged items and 21 initiatives delayed >20% indicate scheduling and delivery risks. Critical gaps: 58 initiatives lack defined baselines and 83% schedule adherence masks underlying delays.
Immediate action required: (1) Establish baselines for all 58 baseline-deficient initiatives within 10 days to enable proper tracking; (2) Conduct root-cause analysis on 21 delayed->20% items and 10 RED/AMBER initiatives to unblock delivery; (3) Accelerate pending-to-active transition of 105 items—current 48% pending rate suggests planning-execution misalignment and cash deployment risk against €39.4M budget authority.

## Slide 3
Portfolio IQ.
DELOITTE AI & DATA
DELOITTE × ENERWAVE
03 / 08
02 · DEEP DIVE: SCHEDULE HEALTH
Schedule Health.
Schedule distribution across 96 active projects
On Track
16
Delayed ≤20%
1
Delayed >20%
21
No Baseline
58
KEY SCHEDULE RISKS
— 105 pending tasks (52% of total 201) risk further schedule delays; 21 tasks already delayed >20% against baseline
— 58 tasks (29%) lack schedule baseline; exposure of €0.9M against €39.4M budget creates planning uncertainty
— 4 overdue tasks with 83% schedule headline completion indicates execution risk in critical path delivery

## Slide 4
Portfolio IQ.
DELOITTE AI & DATA
DELOITTE × ENERWAVE
04 / 08
03 · DEEP DIVE: BUDGET HEALTH
Budget Health.
FY budget distribution by category · €39.4M committed
Long Term Maintenance
€21.5M · 54%
Financial Performance
€13.4M · 34%
Betterment
€3.9M · 10%
Safety / Regulatory
€0.7M · 2%
BUDGET INSIGHTS
191 projects within budget out of 201 total—strong cost control with only 10 RAG-flagged items at €0.9M exposure.
Overrun risk: MEDIUM with 4 overdue projects and 21 delayed >20%, requiring immediate schedule intervention to prevent budget drift.
Exposure headroom: €38.5M available against €39.4M total budget; YTD spend at 3.3% indicates early-stage execution with 58 projects lacking baselines.
Long Term Maintenance dominates at €21.5M (54%) followed by Financial Performance €13.4M (34%), positioning portfolio toward operational resilience over innovation.

## Slide 5
Portfolio IQ.
DELOITTE AI & DATA
DELOITTE × ENERWAVE
05 / 08
04 · LEADERSHIP DECISIONS
Leadership Decisions.
3 items require leadership decision
D1 CRITICAL RESOLVE 105 PENDING INITIATIVES
Activate decision gates on 105 pending initiatives to unblock 52% of portfolio.
105 pending items (52% of 201 total) lack approval. Without resolution by Jan 2026, €39.4M budget allocation remains undefined and 58 initiatives have no baseline.
Owner: Chief Portfolio Officer Target: Jan 2026
D2 HIGH ADDRESS 21 DELAYED INITIATIVES
Conduct recovery review on 21 initiatives delayed >20% to prevent schedule collapse.
21 initiatives (10.4% of active portfolio) exceed 20% schedule variance. Combined with 83% headline schedule health, corrective action must launch by Dec 2025 to prevent Q1 2026 cascade failures.
Owner: Program Management Director Target: Dec 2025
D3 MEDIUM ESTABLISH BASELINES FOR 58 ITEMS
Assign technical baselines to 58 initiatives before Feb 2026 planning cycle.
58 initiatives (29% of portfolio) operate without baseline cost/schedule anchors. YTD spend is only 3.3% of €39.4M budget; baseline gaps prevent proper forecast accuracy and variance trending.
Owner: Portfolio Controls Manager Target: Feb 2026
D4 LOW CLEAR 4 OVERDUE ITEMS
Close or reschedule 4 overdue initiatives to improve portfolio health score.
4 overdue items represent 4% of active work. While low volume, they signal execution discipline. Target completion by Mar 2026 to achieve 95%+ on-time delivery rate.
Owner: Delivery Lead Target: Mar 2026

## Slide 6
Portfolio IQ.
DELOITTE AI & DATA
DELOITTE × ENERWAVE
06 / 08
05 · PROJECTS AT RISK
Projects at Risk.
Top 5 by RAG severity · €0.9M total exposure across 10 flagged
RAG | Project | Owner | Target | CY Budget | %
Red | ST Hydraulic Pumps Replacement | Thisvi | TBD | €168k | 5%
Red | myElpedison Redesign/Relauch Phase 1 (MVP) Design | Commercial | Dec 2025 | €0 | 5%
Red | Strategic spare parts (pending GT turning gear, GT and ST Gen VT/CT) | Thessaloniki | Sep 2024 | €0 | 95%
Amber | Replacement of High Pressure (HP) and Hot Reheat (HRH) Steam turbine valves. | Thessaloniki | Feb 2026 | €360k | 10%
Amber | HRSG HRH Vent stop valve replacement & part of pipeline replacement | Thessaloniki | TBD | €115k | 10%

## Slide 7
Portfolio IQ.
DELOITTE AI & DATA
DELOITTE × ENERWAVE
07 / 08
06 · KEY RISKS
Key Risks.
Top portfolio risks, mitigations and owners
Risk | Severity | Status | Mitigation | Owner | Target
High count of activities with no baseline (58 items) creates schedule and budget visibility gaps, increasing risk of cost overruns and timeline slippage across 96 active projects | HIGH | Active | Establish baselines for all 58 unbaselined activities through structured planning workshops; implement mandatory baseline review gate for project initiation | Program Controls Manager | 2025-02-28
21 activities delayed by >20% indicates systemic scheduling pressure; 105 pending items may cascade delays affecting portfolio completion by Q4 2025 | HIGH | Active | Conduct critical path analysis on delayed activities; reallocate resources to high-impact pending items; implement weekly schedule recovery meetings for Q1 2025 | Schedule Lead | 2025-03-31
Portfolio margin only 0.9€M against 39.4€M budget (2.3% cushion) with 4 overdue items and 10 RAG-flagged activities creates vulnerability to scope changes or contingencies | CRITICAL | Active | Freeze non-critical scope; accelerate completion of overdue/RAG items; establish 5% contingency reserve (1.97€M) by pausing 3 lowest-priority pending initiatives | Portfolio Budget Controller | 2025-01-31

## Slide 8
Portfolio IQ.
DELOITTE AI & DATA
DELOITTE × ENERWAVE
08 / 08
APPENDIX A.1 · RED / AMBER PROJECTS
Flagged Projects.
All 10 Red / Amber projects this period
RAG | Code | Project | Owner | Go-live | Budget | %
Red | 2025-00144 | ST Hydraulic Pumps Replacement | Thisvi | TBD | €168k | 5%
Red | 2025-00040 | myElpedison Redesign/Relauch Phase 1 (MVP) Design | Commercial | Dec 2025 | €0 | 5%
Red | 2025-00095 | Strategic spare parts (pending GT turning gear, GT and ST Gen VT/CT) | Thessaloniki | Sep 2024 | €0 | 95%
Amber | 2025-00188 | Replacement of High Pressure (HP) and Hot Reheat (HRH) Steam turbine valves. | Thessaloniki | Feb 2026 | €360k | 10%
Amber | 2025-00113 | HRSG HRH Vent stop valve replacement & part of pipeline replacement | Thessaloniki | TBD | €115k | 10%
Amber | 2025-00118 | Fuel Gas AGI Flow computer and flow meters replacement | Thessaloniki | TBD | €110k | 80%
Amber | 2025-00157 | Evaporative Cooling Tower (ECT) supply & installation | Thisvi | Dec 2025 | €60k | 5%
Amber | 2025-00116 | ST Lube oil mist eliminator upgrade | Thessaloniki | TBD | €57k | 70%
Amber | 2025-00156 | Addition of oil moisture analyser in GT & ST lube oil tanks | Thisvi | TBD | €30k | 20%
Amber | 2025-00117 | Desuperheaters replacement (HP intermediate and HRH Final) | Thessaloniki | TBD | €0 | 90%